## Sheet1
My Schedual for the entire scenior project
Dates: | Task: | Status:
2022-04-30 | Set up Meteor.js and get Svelte up
2022-08-16 | Start the process of making the IDE part for javascript
2022-09-16 | Start reasearching socket programming with javascript and see more of Meteor.js's features
2022-09-26 | Start the Draft Test Plan
2022-10-01 | Hopefully start the connection to other people via the use of Meteor.js
2022-10-13 | Report my project to the Advisor
2022-10-18 | Start focusing on testing the product extensively, update importaint documents, and start the test document
2022-10-27 | Report my project to the Advisor
2022-11-10 | Report my project to the Advisor
2022-11-20 | Complete the Test plan
2022-11-24 | Report my project to the Advisor
2022-12-05 | Access my progress of the project and make changes if needed
2022-12-08 | Report my project to the Advisor
2022-12-09 | Slowly start programming the visuall aspaect of the project and test the project
2023-01-01 | Start the Defence Documentation Document/ Final Report
2023-01-05 | Start filling the Test Cases that were made
2023-02-12 | Access my progress of the project and make changes if needed
2023-03-01 | The finished project is in the Git Repository
2023-04-05 | Start Setting up the project presentation
2023-04-12 | Present the Final project
Status Key:
Completed
In Progress
Didn't start